Reynalton Residents Association – Annual Action Plan for 2024

| No | Item | Detail | Progress / Actions /Tasks achieved | Completed |
| --- | --- | --- | --- | --- |
| 1 | Community Area | - Trees to be planted - Parking improvements - Clearing area - Improvement of ground - New planting scheme - Upkeep and maintenance - Pathway to Bus Shelter - Drainage for Bus Shelter - Plan of works - Electric cables | - Paint bus shelter |  |
| 2 | Volunteer Lists & Tasks | - Litter Pick - Defib training for residents – Annual? | - 03/03/24 |  |
| 3 | Fire Risk Assessment & Health & Safety Risk Assessment | - Progress Fire Risk Assessment - Produce a H&S Risk Assessment in line with FRA - Actions required as a result of RA | - Utility Door enlarged - Push bar on back exit - Electrics inside – progressing with quotes - Electrics outside in line with community area works |  |
| 4 | Electrical Works and Heaters | - Progress on tender submissions and bid for funds - Works to be undertaken | - Crowd Funding page donations should allow progress for electrical works - 3 more heaters to be purchased and installed |  |
| 5 | Footpath and reinstating the missing bridge | - Footpaths to be reinstated and made useable together with signs | - Bridge installed |  |

| No | Item | Detail | Progress / Actions /Tasks achieved | Completed |
| --- | --- | --- | --- | --- |
| 6 | Village Hall | - Painting kitchen area - Tidying kitchen area |  |  |
| 7 | Events Calendar | - 4-5 events per year | - Events agreed for the year - Dates for each event* Check - Lead agreed for each event |  |
| 8 | Facebook page and Website | - Review as required | - Facebook page and website in place - Calendar on website for bookings | - Completed - Review as required |
| 9 | Ownership of Village Hall & Community Area | - Discuss and progress - Identify Trustees - Establish Constitution - Review with (PAVS) | - Agreement to progress as CIO, voted at AGM |  |
| 10 | Funding & Bids | - What is available? - Agree lead for funding bids |  |  |